## Title Page
ChPP Self-Assessment Tool
V5.0 March 2023

## ProjectOverview
ChPP Self-Assessment Tool
The tool helps you to assess and support your readiness to apply for Chartered Project Professional status under route 1 and route 3 against project experience requirements and professional practice criteria. Please ensure you have read the Chartered Project Professional guidance document prior to completing. You need only type in the pale green shaded cells (columns C to L, rows 13 to 20)
Instructions on how to use this tool - PLEASE READ Enter the names of projects that you feel might be appropriate to demonstrate your project experience in ROW 13 of this, the Project Overview worksheet, starting at COLUMN C. "For your project overview to be successful you must be able to fulfil all the requirements below. The Project Summary and other worksheets will update automatically with the projects that you have identified as meeting all the requirements. As you enter details in the remaining worksheets this will help you identify which projects you might use in your statements, or, where appropriate, areas in which you need to develop your experience in order to be able to demonstrate competence in the future." For each of the worksheets (except Project Summary), place an "X" in the intersecting cells, identifying where you feel you are able to demonstrate your evidence against each project overview requirement and competence assessment criterion. Within your written submission you may reference up to four projects, each competence statement must relate to one project experience overview and meet a minimum of 4 competence criteria. You can’t refer to more than one project experience within a single competence. Suggestion: When an achieved criterion has been selected against a project and ''x'' entered, add ‘New Comment’ (on the right-click or Review tab menu) to the cell and write key notes of how you have achieved the criteria. These comments can be used as a prompt when writing your application. Note: In this document, the term ‘project’ is used to mean those working in project, programme or portfolio management, or in a key control function.
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project name
You must be able to demonstrate;
What you were personally responsible/accountable for.
Show how the project, programme or portfolio demonstrated all of the following characteristics:
Conflicting objectives
High levels of unpredictability or risk
Multiple work packages, projects or programmes;
Multiple interdependent stakeholders
Project Overview Total:

## ProjectSummary
Project Summary Worksheet
Projects that you have entered on the Project Overview worksheet and which you have indicated that the project meets all of the required criteria will appear automatically below.
The Project Summary worksheet will update automatically as you enter details in the remaining competence worksheets, this will help you identify which projects you might use to demonstrate your evidence in your statements, or, where appropriate, areas in which you need to develop your experience in order to be able to demonstrate competence in the future.
x
X
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Totals | Sheet | Name row | Tally row | Column
Project name
You must evidence competence in EITHER 1a or 1b | [14 empty] | D | E | F | G | H | I | J | K | L | M
1a, Budgeting and Cost Control | [11 empty] | BudgetingOrFinancial | 7 | 16
1b, Financial Management | [11 empty] | BudgetingOrFinancial | 22 | 32
You must evidence competence in EITHER 2a or 2b
2a, Change Control | [11 empty] | ChangeControlOrConflictResoluti | 7 | 17
2b, Conflict Resolution | [11 empty] | ChangeControlOrConflictResoluti | 23 | 32
You must evidence competence in EITHER 3a or 3b
3a, Governance Arrangements | [11 empty] | GovernanceArrangementsOrReviews | 7 | 16
3b, Reviews | [11 empty] | GovernanceArrangementsOrReviews | 22 | 32
You must evidence competence in EITHER 4a or 4b
4a, Integrated Planning | [11 empty] | IntegratedPlanningOrSchedul | 7 | 17
4b, Schedule Management | [11 empty] | IntegratedPlanningOrSchedul | 23 | 33
You must evidence competence in EITHER 5a or 5b
5a, Leadership | [11 empty] | LeadershipOrTeamManagement | 7 | 16
5b,Team Management | [11 empty] | LeadershipOrTeamManagement | 22 | 33
You must be able to evidence both of the two competences below
Risk and Issue Management | [11 empty] | RiskAndIssueMgmt | 5 | 14
Stakeholder Engagement & Communication Management | [11 empty] | StakeholderAndCommsMgmt | 5 | 14
You must be able to evidence five of the 16 competences below
Assurance | [11 empty] | Assurance | 5 | 14
Benefits Management | [11 empty] | BenefitsMgmt | 5 | 14
Business Case | [11 empty] | BusinessCase | 5 | 14
Capability Development | [11 empty] | CapabilityDev | 5 | 15
Contract Management | [11 empty] | ContractMgmt | 5 | 14
Diversity and Inclusion | [11 empty] | DiversityInclusion | 5 | 14
Life Cycles | [11 empty] | LifeCycles | 5 | 13
Portfolio Shaping | [11 empty] | PortfolioShaping | 5 | 14
Procurement | [11 empty] | Procurement | 5 | 14
Quality Management | [11 empty] | QualityMgmt | 5 | 13
Requirements Management | [11 empty] | RequirementsMgmt | 5 | 14
Resource Capacity Planning | [11 empty] | ResourceCapPlanning | 5 | 14
Resource Management | [11 empty] | ResourceMgmt | 5 | 12
Solutions Development | [11 empty] | SolutionsDev | 5 | 14
Sustainability | [11 empty] | Sustainability | 5 | 14
Transition Management | [11 empty] | TransitionMgmt | 5 | 14
Totals
Alternative mandatory competences
Mandatory competences
Elective competences

## BudgetingOrFinancial
Alternative mandatory competences
You must evidence competence in EITHER 1a or 1b. You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
Competence 1a Budgeting and cost control
The ability to develop and agree budgets for projects and understanding where costs fall over time. Introduction Budgeting and cost control comprises the estimation of costs, the setting of an agreed budget and management of actual and forecasted costs against the budget.
Professional practice assessment criteria
PP1.1 Established estimates for different project costs
PP1.2 Established and gained agreement to a project budget
PP1.3 Set up funding drawdown arrangements based on cash flow forecasts
PP1.4 Applied metrics to establish cost trends within a project
PP1.5 Refined budget allocations based on cost analysis, applying change control processes as required
PP1.6 Produced financial reports for stakeholders based on financial performance monitoring
PP1.7 Upon project closure, produced final financial reports and distributed them to relevant stakeholders
OR
Competence 1b Financial management
The ability to enable financial resource for delivery and to plan and control the finances of projects, as part of the organisation’s overall financial management, to ensure optimisation of the business case. Introduction Financial management considers the affordability of the proposal within the timeframe and ensures that the money required is secured and made available when needed and is subsequently managed. It provides an interface between the financial management arrangements for a project and the financial systems of the organisation.
Professional practice assessment criteria
PP1.1 Established capital and revenue expenditure for a project whilst ensuring alignment with the organisation’s financial plan
PP1.2 Adopted a consistent approach to the investment appraisal of a project in line with organisational practice
PP1.3 Established control limits for the reporting and approval of budget variances
PP1.4 Arranged for the release of funds at appropriate stages in a project
PP1.5 Established financial reporting milestones and reviews for a project
PP1.6 Ensured a consistent approach to estimating is used across a project
PP1.7 Produced financial progress reports based on the financial information related to a project
PP1.8 Adjusted an organisation’s financial plan based on the progress of a project and associated financial reviews

## ChangeControlOrConflictResoluti
Alternative mandatory competences
You must evidence competence in EITHER 2a or 2b. You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
Competence 2a Change Control
The ability to manage variations and change requests in a controlled way. Introduction Change control is the process through which all requests to alter the baseline scope of projects are identified, evaluated, and then approved, rejected, or deferred.
Professional practice assessment criteria
PP1.1 Established a suitable change control process
PP1.2 Implemented and maintained a suitable change control process
PP1.3 Captured and recorded proposed changes to the agreed project scope
PP1.4 Determined the high-level impact of proposed changes to the project scope including reference to relevant sources
PP1.5 Determined the detailed impact on time and cost estimates of options relating to a proposed change
PP1.6 Reached justified recommendations on the approval, rejection, or deferral of proposed changes to a project and updated stakeholders as necessary
PP1.7 Updated plans and schedules reflecting the approved changes to a project demonstrating configuration management
PP1.8 Used trend analysis to help determine the performance of the current and future projects
OR
Competence 2b Conflict Resolution
The ability to identify, address and resolve differences between individuals and/or interest groups. Introduction Conflict resolution is the process of identifying and addressing differences that, if unmanaged, would affect the delivery of projects and the culture of the workplace. Effective conflict resolution exploits healthy conflict to support group development and learning and addresses negative conflict to prevent differences from becoming harmful elements in a project.
Professional practice assessment criteria
PP1.1 Taken a proactive approach to identifying and addressing potential conflict situations which may have impacted on the project
PP1.2 Taken an impartial approach to investigating the cause of conflict
PP1.3 Evaluated and implemented conflict resolution measures, seeking assistance from others when necessary
PP1.4 Responded appropriately and promptly to conflict situations where intervention was required
PP1.5 Monitored the extent to which conflict resolution measures have been successful
PP1.6 Sought to resolve conflict respecting the views, opinions, and concerns of all parties
PP1.7 Supported others to resolve conflict

## GovernanceArrangementsOrReviews
Alternative mandatory competences
You must evidence competence in EITHER 3a or 3b. You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
Competence 3a Governance Arrangement
The ability to establish and maintain governance structures that define control of deployment for delivery of projects, and that align with organisational practice. Introduction Governance arrangements comprise the framework of authority and accountability that defines and controls the outputs, outcomes and benefits from projects. They are the mechanism whereby the investing organisation exerts financial and technical control over the deployment of the work and the realisation of value
Professional practice assessment criteria
PP1.1 Defined reporting, decision-making hierarchies, and levels of authority for a project
PP1.2 Established the relationship between a project’s governance and the organisation’s governance structures
PP1.3 Designed the project governance structure taking into account context, complexity, and potential impact
PP1.4 Adapted or adjusted the governance structure as required
PP1.5 Ensured clarity of ownership and levels of authority by agreeing the responsibilities and accountabilities with relevant individuals
PP1.6 Ensured effective decision making through maintained governance structures
PP1.7 Ensured effective reporting through maintained governance structures for appropriate staffing and maintenance
OR
Competence 3b Reviews
The ability to manage progression through the life cycle of a project. Introduction Reviews are a way of gathering information to provide an assessment of the status of a project, the ongoing viability of it and determining areas for attention or approval. work, and to supply advice and guidance.
Professional practice assessment criteria
PP1.1 Considered factors which need to be evaluated during a review
PP1.2 Established and implemented a schedule of reviews incorporating key milestones
PP1.3 Obtained appropriate information from valid sources to inform the reviews
PP1.4 Maintained records of any deviations from plans to include reasons for and responses to, the deviations
PP1.5 Communicated the outcomes of reviews to relevant stakeholders
PP1.6 Confirmed stakeholder understanding and acceptance of proposed actions
PP1.7 Implemented agreed actions and updated lessons learned
PP1.8 Conducted and documented a close out review

## IntegratedPlanningOrSchedul
Alternative mandatory competences
You must evidence competence in EITHER 4a or 4b. You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
Competence 4a Integrated Planning
The ability to take forward the definition of outputs into detailed planning, incorporating multiple areas into the integrated project management plan. Introduction Integrated planning involves collating a suite of plans and processes to support a project to create an integrated plan (commonly referred to as the project management plan). Its size, structure and content may vary according to the complexity of the project. The intention is that it captures the fundamental components of scope, quality, time, cost, resources, risks and issues, communication, success and completion criteria and benefits management.
Professional practice assessment criteria
PP1.1 Considered constraints and assumptions when creating an integrated plan
PP1.2 Considered dependencies and governance arrangements, when creating an integrated plan
PP1.3 Demonstrated compliance with organisational practice when establishing the size, structure, and contents of an integrated plan
PP1.4 Included other relevant components, plans and documentation to support a comprehensive integrated plan, and ensured formal acceptance of it
PP1.5 Completed formal sign off and acceptance of an integrated plan
PP1.6 Continually monitored the progress of a project against the integrated plan
PP1.7 Adjusted the integrated plan utilising a change control process
PP1.8 Applied configuration management to a plan once it had been formally accepted
OR
Competence 4b Schedule Management
The ability to undertake time-based planning with an emphasis on activities and resource. Introduction Schedule management is the process of developing and maintaining schedules that show when work for a specific project is planned to be performed. It considers any dependencies and can be for internal and/or external resources and activities.
Professional practice assessment criteria
PP1.1 Defined tools and techniques for creating and updating a schedule
PP1.2 Established units of measure to accurately define activities and events to be completed during a project
PP1.3 Developed duration estimates and critical dates for each activity and event
PP1.4 Determined relationships and dependencies between activities and events, when constructing a schedule
PP1.5 Documented a schedule of phases, milestones, and reviews to support project monitoring and progress reporting
PP1.6 Agreed a schedule baseline, exceptions, and tolerance thresholds
PP1.7 Communicated regular schedule updates to internal or external stakeholders
PP1.8 Refined a schedule of activities based on effective monitoring, implementing the change control process when required

## LeadershipOrTeamManagement
Alternative mandatory competences
You must evidence competence in EITHER 5a or 5b. You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
Competence 5a Leadership
The ability to empower and inspire others to deliver successful projects by providing vision, direction, feedback, and support, so that people can do their best work. Introduction Leadership is essential to the successful management of projects. It requires clear communication of vision, values, and objectives. Leadership styles need to be adapted to create a supportive working environment that builds trust, through coaching and mentoring that is engaging and empowering for the individual.
Professional practice assessment criteria
PP1.1 Maintained a team’s understanding of, and commitment to the vision, values, and objectives of a project
PP1.2 Selected an appropriate leadership style based on the situation and/or context
PP1.3 Collaborated with others to maintain the momentum of a project
PP1.4 Encouraged others to adopt behaviours which built trust, confidence, and collaboration either within or between teams
PP1.5 Established environments which presented opportunities for empowered and autonomous working
PP1.6 Established leadership approaches to work with remote teams, colleagues and stakeholders
PP1.7 Identified and addressed difficulties and challenges through facilitating open discussions in a timely manner
OR
Competence 5b Team Management
The ability to select, develop and manage individuals to create and sustain teams. Introduction Team management entails bringing people together and motivating, co-ordinating and developing them to achieve specified objectives that cannot be realised individually. It involves encouraging team members, internal and external, to work in collaboration towards achieving a common goal. The success of any project is dependent on effective team management.
Professional practice assessment criteria
PP1.1 Agreed team objectives and ways of working to achieve the vision and goals of a project
PP1.2 Evaluated the maturity level of the team
PP1.3 Adopted a proactive approach to communication to establish networks of support and facilitate effective ownership of delegated tasks
PP1.4 Built a relationship of trust and support, taking into consideration the possible complexities of collaboration, virtual working, time zones and cultures
PP1.5 Met the demands of a project through balancing individual and team needs
PP1.6 Provided opportunities for coaching and/or mentoring to members of a team, creating an environment of learning and trust thus promoting continual professional development
PP1.7 Addressed performance issues likely to negatively impact on the success of a project whilst remaining alert to any signs of stress within the team
PP1.8 Acknowledged levels of performance through constructive feedback to individuals and teams and celebrated success when evident
PP1.9 Established a learning culture and promoted continued professional development

## RiskAndIssueMgmt
Mandatory Competence 6 - Risk and issue management
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to identify and monitor risks (threats and opportunities) and issues; to plan and implement responses to those risks and respond to issues that affect a project. Introduction Risk management is the proactive process to identify, assess and respond appropriately to risks. Examples of risk management includes discerning which threats to actively minimise, and opportunities to maximise or pursue. Issue management is about having the flexibility to react to issues in ethical and appropriate ways, including escalation to the appropriate authority.
Professional practice assessment criteria
PP1.1 Continually identified risks within a project
PP1.2 Created a risk register including potential impact and suitable responses
PP1.3 Assessed the probabilities and impacts of risks and planned their responses
PP1.4 Capture and recorded issues, how they were resolved, and their implications to inform planning for future projects
PP1.5 Reacted, assessed, and planned responses to issues
PP1.6 Implemented responses to risks and issues including escalation, recording lessons learned
PP1.7 Transferred and/or formally closed unresolved risks at the end of a project or phase

## StakeholderAndCommsMgmt
Mandatory Competence 7 - Stakeholder Engagement and Communications Management
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to work with people, both internally and externally, to build support to achieve intended outcomes. Introduction Stakeholder engagement is understanding who needs to be engaged and influenced and ensuring ongoing commitment. Communication management ensures the exchange of relevant and timely information to support the successful delivery of a project and inform decision making.
Professional practice assessment criteria
PP1.1 Determined stakeholder interests, and levels of influence for a project
PP1.2 Produced a communication plan and undertaken effective stakeholder engagement based upon it
PP1.3 Monitored effectiveness of the communication plans and stakeholder engagement activities
PP1.4 Adjusted the communication plan and responded to any changing stakeholder engagement needs
PP1.5 Employed relevant communication methods and media to meet stakeholder requirements and expectations
PP1.6 Disseminated clear, timely and relevant information to stakeholders
PP1.7 Obtained, and responded to, feedback from stakeholders which may have an impact on a project

## Assurance
Elective Competence 8 - Assurance
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to provide confidence to the governance board that a project is on track to deliver the objectives and intended value. Introduction Assurance is objective and independent, working in partnership with governance and risk management.
Professional practice assessment criteria
PP1.1 Agreed the scope and responsibilities for assurance activities
PP1.2 Resourced assurance activities
PP1.3 Conducted assurance activities making recommendations for corrective action where required
PP1.4 Prioritised assurance activities
PP1.5 Provided advice, guidance, and support in the implementation of recommendations
PP1.6 Maintained effective communication with stakeholders to address concerns and report on corrective actions
PP1.7 Analysed patterns of change to identify trends to improve current or future project performance

## BenefitsMgmt
Elective Competence 9 - Benefits Management
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to identify and agree the benefits and determine how they will be measured, monitored, and managed throughout a project until they are realised. Introduction Benefits management actively documents, measures, and monitors a project to assure realisation. It aligns with the business case and intended outcomes for delivery.
Professional practice assessment criteria
PP1.1 Demonstrated how the intended benefits relate to strategic objectives and are measurable to stakeholders
PP1.2 Created a benefits management strategy which considers priorities, timescales and responsibilities, and monitoring methods
PP1.3 Confirmed dependencies between intended benefits and the outputs, outcomes, and related business changes
PP1.4 Created a benefits realisation plan which considers funding options, key indicators, milestones, and reporting schedules
PP1.5 Prioritised benefits based on their level of contribution to strategic objectives
PP1.6 Carried out effective monitoring against the benefits realisation plan
PP1.7 Responded to the changing project context by adjusting actions to maximise benefits realisation

## BusinessCase
Elective Competence 10 - Business Case
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to prepare, gain approval of, refine and update business cases that justify the initiation, investment and/or continuation of projects in terms of benefits, costs, and risks. Introduction Business cases provide the justification for undertaking and continuing with a project. The business case needs to be reconsidered at regular review points during a project in case the original justifications are affected by later developments.
Professional practice assessment criteria
PP1.1 Supported a persuasive argument for a business case through the effective analysis of relevant factors
PP1.2 Determined the relevant factors which could influence the development of a business case
PP1.3 Documented a business case in a relevant format
PP1.4 Established a benefits framework for a business case
PP1.5 Gained initial and ongoing formal acceptance of a business case.
PP1.6 Implemented a change control process and configuration management system when updating a business case
PP1.7 Monitored and refined a business case as circumstances and factors demanded

## CapabilityDev
Elective Competence 11 - Capability Development
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to assess organisational maturity in relation to a project and the wider organisation. Introduction Capability development addresses the continuous improvement of competences within an organisation, investing in people and knowledge, and improving the predictability of delivering results and creating the correct context for teams to perform.
Professional practice assessment criteria
PP1.1 Conducted a skills analysis for individuals within an organisation to identify gaps in competences required to deliver a project
PP1.2 Used tools and techniques to determine an organisation’s capability to support skills development
PP1.3 Created or adapted a training and development strategy in relation to project management
PP1.4 Implemented a training and development strategy in relation to project management
PP1.5 Developed or adapted competency models to an organisation’s workforce in relation to project management
PP1.6 Monitored and evaluated organisational learning against the capability development objectives
PP1.7 Adapted the strategy and model to the needs of a changing environment
PP1.8 Embedded an on-going learning culture in the organisation

## ContractMgmt
Elective Competence 12 - Contract Management
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to monitor and manage supplier performance. Introduction Contract management is a proactive activity tailored to the size, complexity, and significance of a project. Appropriate contract management will facilitate a proactive working environment and include a process to review progress, incorporating formalised reporting from contract initiation through to contract closure.
Professional practice assessment criteria
PP1.1 Monitored client performance against their agreed contractual obligations
PP1.2 Complied with your organisational procedures associated with contract management
PP1.3 Monitored the supplier performance against their agreed contractual obligations
PP1.4 Managed supplier relationships
PP1.5 Took appropriate action where necessary to ensure all parties comply with the terms of a contract
PP1.6 Managed contract variances to address any potential contractual items
PP1.7 Closed a contract and reported outcomes to stakeholders

## DiversityInclusion
Elective Competence 13 - Diversity and Inclusion
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to build and maintain an inclusive environment that embraces a diverse culture. Introduction Diversity and inclusion need to be considered as workplace environments are increasingly made up of individuals with different backgrounds, needs, abilities and ways of working. There is an opportunity within projects to proactively address the institutionalised inequalities that may exist, by being aware and treating people fairly.
Professional practice assessment criteria
PP1.1 Proactively researched different aspects of diversity and how these can impact individuals at work
PP1.2 Actively identified and engaged with diverse skill sets and individual traits that constitute a team
PP1.3 Recognised the potential effects of personal bias and cultural norms that may be influential on perspective and judgement
PP1.4 Created and sustained a positive, inclusive working environment and identified opportunities for inclusion
PP1.5 Maximised the opportunities presented by a diverse team and led them to a common purpose
PP1.6 Established a cohesive culture that supported both organisational governance and appropriate values and behaviours
PP1.7 Actively explored and responded to signs of bias that could impact individual and/or team cohesion and performance

## LifeCycles
Elective Competence 14 - Life Cycles
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to structure and organise projects. Introduction A life cycle is a framework comprising a series of distinct stages required to transform an idea or concept into reality in an orderly and efficient manner. A life cycle can be viewed as the structure underpinning deployment. Recognised life cycles include: linear (commonly referred to as waterfall), iterative (commonly referred to as agile) and hybrid. The choice of life cycle depends on the desired outputs, outcomes, benefits, and the expected uncertainty, novelty, and risk appetite for a project.
Professional practice assessment criteria
PP1.1 Identified the underlying principles of a life cycle for management of projects within the organisation
PP1.2 Analysed potential life cycles available for the management of a project
PP1.3 Investigated the impact of internal or external factors which influenced adoption of an alternate life cycle approach to the organisation’s established practice
PP1.4 Adapted or refined an existing life cycle approach to reflect size, complexity and significance of a project
PP1.5 Utilised existing or developed sources of information to inform the processes, standards and guidelines required to implement the life cycle
PP1.6 Reflected on the strengths and limitations of a framework/methodology making refinements as required based on experience

## PortfolioShaping
Elective Competence 15 - Portfolio Shaping
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to set up portfolios to ensure efficient delivery of strategic objectives. Introduction Portfolio shaping is the grouping of projects at an organisational or functional level to select, prioritise and control deployment in line with strategic objectives and the capacity to deliver, balancing projects and business-as-usual, while optimising return on investment.
Professional practice assessment criteria
PP1.1 Determined changes required by the organisation’s strategic objectives
PP1.2 Categorised a range of related projects which address an organisation's strategic objectives using a mapping of intended outputs, outcomes, and benefits
PP1.3 Determined gaps which may exist in the alignment of projects and programmes, either current or proposed to strategic objectives
PP1.4 Established measures to compare the likely value of a portfolio to an organisation’s strategic objectives
PP1.5 Applied measures to prioritise current and proposed projects and programmes, considering the availability of finance and other resources when applying those measures
PP1.6 Recommended where projects are initiated, maintained, or closed to maintain a balanced portfolio
PP1.7 Communicated to stakeholder’s recommendations to inform decisions about the maintenance of a balanced portfolio

## Procurement
Elective Competence 16 - Procurement
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to secure the provision of resources, choosing strategies for obtaining best value from supply chains. Introduction Procurement is the process for securing the goods and services that are required from external suppliers to satisfy project needs as appropriate.
Professional practice assessment criteria
PP1.1 Developed detailed specifications for the procurement of resources for a project
PP1.2 Agreed a procurement strategy with relevant stakeholders
PP1.3 Established the type, quality, and quantity of the resource requirement
PP1.4 Evaluated technical and commercial options for fulfilling the requirements
PP1.5 Agreed contracts and statements of work in line with organisational requirements
PP1.6 Negotiated and secured resources to effectively deliver a project
PP1.7 Complied with organisational procedures when selecting and negotiating with suppliers

## QualityMgmt
Elective Competence 17 - Quality Management
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to ensure that outputs are delivered in accordance with requirements. Introduction Quality management ensures that the outputs from the defined scope and the processes through which they are delivered are meeting stakeholder requirements and are fit for purpose.
Professional practice assessment criteria
PP1.1 Established agreed quality criteria for the processes and outputs of the project with reference to the business case and project plans
PP1.2 Created or adapted a quality management plan involving stakeholders and reflecting the organisation’s processes, culture, and values
PP1.3 Managed quality assurance in accordance with the Quality Management Plan
PP1.4 Managed quality control in accordance with the Quality Management Plan
PP1.5 Managed outcomes from the quality management process, implementing the change control process where required
PP1.6 Captured lessons learned during a project to contribute to continuous improvement

## RequirementsMgmt
Elective Competence 18 - Requirements Management
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to prepare and maintain definitions of the requirements of projects. Introduction Requirements management is the process of capturing, assessing, and justifying stakeholders’ wants and needs to satisfy an identified need. Comprehensive and measurable requirements are critical to the success of a project.
Professional practice assessment criteria
PP1.1 Conducted an analysis of stakeholder wants and needs to inform a schedule of requirements
PP1.2 Confirmed the outcomes of research through internal and/or external experts
PP1.3 Prioritised stakeholder wants, and needs based on research
PP1.4 Determined the dependencies and constraints which influenced the delivery of the requirements
PP1.5 Documented the requirements agreed within the schedule of requirements
PP1.6 Finalised a schedule of requirements based on negotiation with stakeholders
PP1.7 Adjusted and approved a schedule of requirements during a project

## ResourceCapPlanning
Elective Competence 19 - Resource Capacity Planning
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to plan resource needs in line with the strategic direction of the organisation to ensure that resource utilisation is maintained at an appropriate level for optimal efficiency. Introduction Resource capacity planning looks at the strategic direction of the organisation, to create a forecast of the skills, capabilities and resources required to deliver future needs. This activity is typically delivered by a programme and/or portfolio manager.
Professional practice assessment criteria
PP1.1 Established resource requirements for a project
PP1.2 Included consideration of other projects when planning the allocation of resources
PP1.3 Assessed the total resource capacity for the duration of the project
PP1.4 Capitalised on opportunities for sharing infrastructure and/or procurement efficiencies
PP1.5 Governed the direction of project activities through effective scheduling of phases, milestones, and review points
PP1.6 Established reporting requirements for resource utilisation
PP1.7 Prepared and delivered progress reports to relevant stakeholders

## ResourceMgmt
Elective Competence 20 - Resource Management
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to acquire and deploy internal and external resources. Introduction Resource management is the process of identifying and scheduling the resources required to implement a project, while acknowledging the need to use scarce resources in an optimal way.
Professional practice assessment criteria
PP1.1 Determined major resource drivers or constraints within a project
PP1.2 Established resource requirements for all activities and events within a project.
PP1.3 Determined internal resources which are available to support the delivery of a project considering their availability.
PP1.4 Determined external resources which are available to support the delivery of a project considering their availability.
PP1.5 Prepared a schedule for resource use, reconciling resource limits and time constraints.
PP1.6 Monitored resource use against a schedule during a project and identify variances that require action.
PP1.7 Refined a resource schedule using a change control process.

## SolutionsDev
Elective Competence 21 - Solutions Development
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to determine the optimal solution to satisfy agreed requirements. Introduction Solutions development is the process of ensuring that there is clarity on the problem to be solved, and then of exploring multiple options until a preferred solution is identified and subsequently maintained and refined.
Professional practice assessment criteria
PP1.1 Used tools and techniques to identify options to satisfy project requirements
PP1.2 Used tools and techniques to evaluate and select options develop solutions
PP1.3 Documented options and agreed a preferred solution aligned with project governance
PP1.4 Communicated the rationale for agreed solutions to stakeholders
PP1.5 Implemented a monitoring process and refined solutions as required
PP1.6 Implemented a change control process to manage solution refinement
PP1.7 Utilised a configuration management process for refinement of solutions

## Sustainability
Elective Competence 22 - Sustainability
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to balance the environmental, social, economic, and administrative considerations that will impact a project. Introduction Sustainability involves taking individual and organisational responsibility to ensure outputs, outcomes and benefits are sustainable over their life cycles, meeting the current needs of stakeholders without compromising or over burdening future generations. In addition, change initiatives need to be delivered through sustainable working practices and methods. Sustainability is so significant and important, that projects need to proactively alter behaviours and apply methods that ensure these considerations become second nature.
Professional practice assessment criteria
PP1.1 Promoted and adhered to sustainable working practices that support organisational standards
PP1.2 Determined the sustainability vision and objectives for a project and assessed ways to achieve them
PP1.3 Established stakeholder perception and actively managed sustainability expectations and outcomes
PP1.4 Employed techniques to embed a culture of sustainability within a project and applied a range of communication styles to promote sustainability objectives
PP1.5 Monitored sustainability measures being undertaken, ensuring stakeholders remain informed and supportive
PP1.6 Promoted the sharing of lessons learned and encouraged sustainability and accountability at all levels
PP1.7 Monitored emergent sustainability initiatives and promoted efficiencies to facilitate sustainability in a project or organisation

## TransitionMgmt
Elective Competence 23 - Transition Management
You are looking to demonstrate a minimum of 4 criteria within the competence against a project.
The ability to manage the integration of the outputs of a project into business-as-usual (BAU), ensuring that outputs enable delivery of the intended value. Introduction Transition management is multi-faceted, its purpose being to facilitate changed capability, bedding in new processes, practices, and tools and techniques. It includes organisational change management and directing benefits realisation management.
Professional practice assessment criteria
PP1.1 Determined key staff required to support a transition process.
PP1.2 Established the logistics requirements to support a transition process
PP1.3 Determined the knowledge transfer requirements for a transition process
PP1.4 Created a plan including transition priorities, ownership, and potential for disruption
PP1.5 Negotiated with stakeholders to gain agreement on the transition process
PP1.6 Negotiated agreement on staffing solutions, logistics and knowledge transfer requirements
PP1.7 Established a benefit review process to monitor benefits realisation which meets the requirements of relevant stakeholders